STREAMLINING IT PROCUREMENT

Automating Standard Laptop Orders with Flow Designer

| Team ID | SWTID-2026-3408 |
| --- | --- |
| Project Phase | Planning & Sprint Estimation |
| Prepared Date | 03 October 2026 |

1. Project Objective

The project aims to automate the standard laptop procurement process using ServiceNow Flow Designer. The solution will provide a standard catalog request, apply approval rules, create procurement or fulfillment tasks, and notify the requester throughout the process.

2. Planning Logic

| Term | Meaning |
| --- | --- |
| Sprint | A fixed period in which the team completes a planned set of tasks. |
| Epic | A large project requirement that is divided into smaller user stories. |
| User Story | A small requirement or task that forms part of an Epic. |
| Story Point | A relative measure of effort required to complete a user story. |

Story Point Scale: 1 = Very Easy | 2 = Normal | 3 = Moderate | 5 = Difficult

3. Sprint 1 – Requirement Analysis & Catalog Setup

| Epic | User Story | ID | Story Points |
| --- | --- | --- | --- |
| Requirement Analysis (Epic 1) | Identify standard laptop models | USN1 | 2 |
| Requirement Analysis (Epic 1) | Define approval rules and policies | USN2 | 1 |
| Catalog Setup (Epic 2) | Create standard laptop catalog item | USN3 | 3 |
| Catalog Setup (Epic 2) | Configure request form and variables | USN4 | 3 |
| Catalog Setup (Epic 2) | Set up roles and approval groups | USN5 | 3 |

Sprint 1 Total = 2 + 1 + 3 + 3 + 3 = 12 Story Points.

4. Sprint 2 – Flow Automation, Testing & Deployment

| Epic | User Story | ID | Story Points |
| --- | --- | --- | --- |
| Flow Automation (Epic 3) | Trigger flow on catalog request | USN6 | 2 |
| Flow Automation (Epic 3) | Add approval action | USN7 | 2 |
| Flow Automation (Epic 3) | Create procurement / fulfillment task | USN8 | 2 |
| Flow Automation (Epic 3) | Send notification to requester | USN9 | 4 |
| Testing (Epic 4) | End-to-end testing of the flow | USN10 | 5 |
| Deployment (Epic 5) | Deploy and document the solution | USN11 | 5 |

Sprint 2 Total = 2 + 2 + 2 + 4 + 5 + 5 = 20 Story Points.

5. Velocity Calculation

| Sprint 1 | 12 Story Points |
| --- | --- |
| Sprint 2 | 20 Story Points |
| Total | 32 Story Points |
| Average Velocity | 32 / 2 = 16 Story Points per Sprint |

PROJECT PLANNING PHASE

Product Backlog, Sprint Schedule & Estimation

6. Product Backlog

| Sprint | Functional Requirement (Epic) | User Story | User Story / Task | Points | Priority |
| --- | --- | --- | --- | --- | --- |
| Sprint 1 | Laptop Request Catalog | USN-1 | As an employee, I can submit a standard laptop request through the catalog. | 2 | High |
| Sprint 1 | Laptop Request Catalog | USN-2 | As an employee, I receive a confirmation after submitting my request. | 2 | High |
| Sprint 1 | Laptop Request Catalog | USN-3 | As an IT admin, I can define standard laptop models and configurations. | 3 | High |
| Sprint 1 | Flow Designer Automation | USN-4 | As an IT admin, I can build a flow triggered by a catalog request. | 5 | High |
| Sprint 1 | Flow Designer Automation | USN-5 | As an IT admin, the flow checks employee eligibility and laptop rules. | 5 | High |
| Sprint 1 | Flow Designer Automation | USN-6 | As an employee, I can view the status of my laptop request. | 2 | Medium |
| Sprint 2 | Approval Automation | USN-7 | As a manager, I receive an approval request automatically through the flow. | 5 | High |
| Sprint 2 | Approval Automation | USN-8 | As an IT admin, manager responses update the request automatically. | 3 | High |
| Sprint 2 | Approval Automation | USN-9 | As a manager, I receive reminders when approval is pending. | 2 | Medium |
| Sprint 2 | Fulfillment Processing | USN-10 | As a procurement officer, I can create a fulfillment task after approval. | 5 | High |
| Sprint 2 | Fulfillment Processing | USN-11 | As a procurement officer, stock availability is checked before an order is placed. | 3 | Medium |
| Sprint 3 | Order Fulfillment | USN-12 | As a procurement officer, approved orders are sent to the vendor automatically. | 5 | High |
| Sprint 3 | Order Fulfillment | USN-13 | As an asset manager, an asset record is created automatically when the item is received. | 5 | High |
| Sprint 3 | Notifications & Tracking | USN-14 | As an employee, I am notified about shipment and expected delivery. | 3 | Medium |
| Sprint 3 | Notifications & Tracking | USN-15 | As an IT admin, I can track flow status and identify delays. | 4 | Medium |
| Sprint 3 | Notifications & Tracking | USN-16 | As an employee, I can confirm receipt of my laptop. | 3 | Low |
| Sprint 4 | Reporting & Analytics | USN-17 | As an IT manager, I can view a dashboard of requests, approvals and fulfillment cycle times. | 5 | Medium |
| Sprint 4 | Reporting & Analytics | USN-18 | As an IT manager, I can identify repeated delays and exceptions. | 3 | Low |
| Sprint 4 | Testing & Deployment | USN-19 | As a user, I can perform end-to-end testing and verify acceptance criteria. | 5 | High |
| Sprint 4 | Testing & Deployment | USN-20 | As a team, we know the flow and catalog item are ready for production using an update set. | 4 | High |
| Sprint 4 | Testing & Deployment | USN-21 | As a team, we document the flow design and support procedure. | 3 | Medium |

7. Additional Planning Notes

Acceptance criteria should be checked before a story is marked complete.

Approval, fulfillment and notification steps should be tested with both approved and rejected requests.

The final deployment should include documentation of the catalog item, flow, approvals and support procedure.

8. Project Tracker, Velocity & Burndown Plan

| Sprint | Total Story Points | Planned Days | Sprint Start | Planned End | Status |
| --- | --- | --- | --- | --- | --- |
| Sprint 1 | 20 | 6 Days | 05 Oct 2026 | 10 Oct 2026 | Planned |
| Sprint 2 | 20 | 6 Days | 12 Oct 2026 | 17 Oct 2026 | Planned |
| Sprint 3 | 20 | 6 Days | 19 Oct 2026 | 24 Oct 2026 | Planned |
| Sprint 4 | 20 | 6 Days | 26 Oct 2026 | 31 Oct 2026 | Planned |

9. Velocity

Velocity represents the amount of planned work a team can complete in one sprint. For the two-sprint implementation plan above, the calculated average velocity is 16 story points per sprint (32 total story points ÷ 2 sprints). The later backlog sprints can be re-estimated using the team's actual completed work.

10. Burndown Chart Plan

A burndown chart tracks remaining work against the planned sprint timeline. The ideal line decreases steadily from the initial story-point total to zero by the sprint end. Actual progress can be updated at the end of each working day.

| Day | Planned Remaining Points | Actual Remaining Points |
| --- | --- | --- |
| Day 1 | 20 | — |
| Day 2 | 16 | — |
| Day 3 | 12 | — |
| Day 4 | 8 | — |
| Day 5 | 4 | — |
| Day 6 | 0 | — |

11. Expected Outcome

The completed solution should provide a standardized laptop ordering experience with automated approvals, procurement/fulfillment task creation, requester notifications, testing evidence and deployment documentation.

12. Reference

ServiceNow Flow Designer and Service Catalog documentation can be used as supporting references while implementing the solution.